## Sheet1
引用编号 | 版本 | 冲刺号 | 分类 | 标题 | 故事 | 类型 | 进度 | 初始估计（h） | 优先级 | 如何演示 | 商业价值 | 理想时间（h） | 调整因子 | 复杂度 | 信息度 | 备注
1 | 1 | 1 | user story | 登录系统 | 作为小鸽快跑用户，我希望可以登录系统，以便我可以使用系统。 | Initial Feature | Not Done | 2 | 98 |  |  | 2
2 | 1 | 1 | user story | 验证登录消息 | 作为小鸽快跑用户，我希望可以验证我的登录信息，以便防止非本人登录我的账户。 | Initial Feature | Not Done | 1 | 96 |  |  | 1 | #REF!
3 | 1 | 1 | user story | 设置保密信息 | 作为小鸽快跑用户，我希望可以设置保密信息，以便我可以及时找回丢失的密码。 | Initial Feature | Not Done | 3 | 95 |  |  | 3
4 | 1 | 1 | user story | 制定跑步计划 | 作为小鸽快跑用户，我希望可以制定跑步计划，以便我及时完成与查看。 | Initial Feature | Not Done | 1 | 93 |  |  | 1 | #REF!
5 | 1 | 1 | user story | 积分 | 作为小鸽快跑用户，我希望可以保存我的积分，以便我及时查看。 | Initial Feature | Not Done | 1 | 93 |  |  | 2 | #REF!
6 | 1 | 1 | user story | 匹配好友 | 作为小鸽快跑用户，我希望可以匹配好友并添加，以便我可以进行聊天以及共同跑步 | Initial Feature | Not Done | 0.5 | 90 |  |  | 1 | #REF!
7 | 1 | 1 | user story | 分享 | 作为小鸽快跑用户，我希望可以分享跑步的轨迹，以便在社区中进行分享。 | Initial Feature | Not Done | 2 | 90 |  |  | 2 | #REF!
8 | 1 | 1 | user story | 点赞 | 作为小鸽快跑用户，我希望可以在社区中点赞，以便查看社区中其他用户的跑步信息。 | Initial Feature | Not Done | 3 | 88 |  |  | 3 | #REF!
9 | 1 | 1 | user story | 评价 | 作为小鸽快跑用户，我希望可以在社区中评价，以便可以在社区中发表自己的评论。 | Initial Feature | Not Done | 0.5 | 85 |  |  | 1 | 0
10 | 1 | 1 | user story | 转发 | 作为小鸽快跑用户，我希望可以在社区中转发，以便可以发送给自己的好友。 | Initial Feature | Not Done | 2 | 80 |  |  | 2
Generate index cards
Note on A1: Luc Segers: This reference ID should be unique. This number is used throughout the whole worksheet so be aware.
Note on B1: Luc Segers: This is the release where the story will be developped
Note on C1: Luc Segers: This is the sprint where the story will be developped
Note on D1: Luc Segers: This is a category to which the story belongs. Example : Infrastrucuture, Back-End, Animation, ...
Note on F1: Luc Segers: This is the story (Feature, Epic, User). Depending on in which phase you are in (Présales, Scope, …) the detail could be higher. Normally you could describe a user story as follow: As a <Role> I can do <this> and the result is <that> ... Offcourse this is not always possible, so you should be creative. A story should conduct to the following rules: I = Independent N = Negotiable V = Valuable to customer E = Estimatable S = Small T = Testable
Note on G1: Luc Segers: Type of the story.
Note on H1: Luc Segers: Status of the story
Note on I1: Luc Segers: This column is calculated: Ideal Hours * Adjustment Factor
Note on J1: Luc Segers: M = Must Have S = Should Have C = Could Have W = Won't have this time
Note on L1: Luc Segers: 0 = Lowest Business Value 100 = Highest Business Value
Note on M1: Luc Segers: Enter here the new ideal estimates which are done with planningpoker
Note on N1: Luc Segers: This column is calculated based on the values of complexity and information. The data is looked up in the setup tab.
Note on O1: Luc Segers: Complexity 0 = Not Defined 1 = Very Simple 2 = Simple 3 = Moderate 4 = Complex 5 = Extreme Complex
Note on P1: Luc Segers: Information 0 = Not Defined 1 = No information 2 = Little information 3 = Moderate information 4 = Much information 5 = All information