## Sheet1
引用编号 | 版本 | 冲刺号 | 分类 | 标题 | 故事 | 类型 | 进度 | 初始估计（h） | 优先级 | 如何演示 | 商业价值 | 理想时间（h） | 调整因子 | 复杂度 | 信息度 | 备注
1 | 1 | 1 | user story | 最热音乐推荐 | 作为一个偶尔听歌的用户，我希望能够有一个最热歌曲推荐，以便于减轻我选歌的困惑。 | Initial Feature | Not Done | 2 | 98 |  |  | 2
2 | 1 | 1 | user story | 每周音乐排行榜 | 作为一个用户，我希望能看到每周的歌曲排行榜，以便跟随潮流 | Initial Feature | Not Done | 1 | 96 |  |  | 1 | 0
3 | 1 | 1 | user story | 音乐收藏列表 | 作为一个用户，我希望能有一个音乐收藏列表，以便于收藏自己喜欢的音乐 | Initial Feature | Not Done | 3 | 95 |  |  | 3
4 | 1 | 1 | user story | 音乐分享平台 | 作为一个用户我希望，能有一个音乐分享平台，供我们分享自己喜欢的音乐 | Initial Feature | Not Done | 1 | 93 |  |  | 1 | 0
5 | 1 | 1 | user story | 音乐喜好推荐 | 作为一个用户，我希望能有一个音乐推荐功能，根据个人喜好推荐相应风格的歌曲 | Initial Feature | Not Done | 1 | 93 |  |  | 2 | 0
6 | 1 | 1 | user story | 播放显示歌词 | 作为一个用户，我希望能在播放音乐时，显示相应的歌词 | Initial Feature | Not Done | 2 | 90 |  |  | 2
7 |  | 1 | user story | 音乐订阅 | 作为运营商，我希望能通过用户的订阅来给用户推荐相应歌手，或风格的歌曲，以提高用户的满意程度 | Initial Feature | Not Done | 1 | 90 |  |  | 1
8 | 1 | 1 | user story | 网银充值 | 作为一个用户，我希望可以通过网银快速充值积分。 | Initial Feature | Not Done | 3 | 88 |  |  | 3 | 0
9 | 1 | 1 | user story | 快速搜索音乐 | 作为一个发烧音乐用户，我希望能够通过音乐名、歌手等搜索歌曲，以便于快速定位为想听的歌曲 | Initial Feature | Not Done | 0.5 | 85 |  |  | 1 | 0
10 | 1 | 1 | user story | QQ登录 | 作为一个用户，我希望能够通过QQ登录，以便于更快捷的登录系统，而省去注册环节。 | Initial Feature | Not Done | 2 | 80 |  |  | 2
Note on A1: Luc Segers: This reference ID should be unique. This number is used throughout the whole worksheet so be aware.
Note on B1: Luc Segers: This is the release where the story will be developped
Note on C1: Luc Segers: This is the sprint where the story will be developped
Note on D1: Luc Segers: This is a category to which the story belongs. Example : Infrastrucuture, Back-End, Animation, ...
Note on F1: Luc Segers: This is the story (Feature, Epic, User). Depending on in which phase you are in (Présales, Scope, …) the detail could be higher. Normally you could describe a user story as follow: As a <Role> I can do <this> and the result is <that> ... Offcourse this is not always possible, so you should be creative. A story should conduct to the following rules: I = Independent N = Negotiable V = Valuable to customer E = Estimatable S = Small T = Testable
Note on G1: Luc Segers: Type of the story.
Note on H1: Luc Segers: Status of the story
Note on I1: Luc Segers: This column is calculated: Ideal Hours * Adjustment Factor
Note on J1: Luc Segers: M = Must Have S = Should Have C = Could Have W = Won't have this time
Note on L1: Luc Segers: 0 = Lowest Business Value 100 = Highest Business Value
Note on M1: Luc Segers: Enter here the new ideal estimates which are done with planningpoker
Note on N1: Luc Segers: This column is calculated based on the values of complexity and information. The data is looked up in the setup tab.
Note on O1: Luc Segers: Complexity 0 = Not Defined 1 = Very Simple 2 = Simple 3 = Moderate 4 = Complex 5 = Extreme Complex
Note on P1: Luc Segers: Information 0 = Not Defined 1 = No information 2 = Little information 3 = Moderate information 4 = Much information 5 = All information